## APPENDIX TO TENDER FINANCIAL OFFER

|  | Sub-Clauses of Conditions of Contract (as amended in Particular Conditions) |  |
| --- | --- | --- |
| Employer's name and address (Employer) | 1.1.2.2 & 1.3 | Ministry for Public Investment No 11 Nemanjina Street 11000 Belgrade, Serbia Employer’s mail address: ”Ministry for Public Investment” Nemanjina street no. 22-26, Belgrade, Administration for Joint Services of the Republic Bodies registry 11000 Belgrade Serbia |
| Contractor's name and address | 1.1.2.3 & 1.3 | (to be inserted) |
| Name and address of the Engineer | 1.1.2.4 & 1.3 | < if known at the time of tendering to be identified otherwise write (to be inserted)> |
| Time for Completion of the whole Works | 1.1.3.3 | 1100 calendar days from Commencement Date to Notice of Completion. The Commencement date is defined in accordance with sub-clause no. 8.1 of the Particular Conditions of Contract. |
| Defects Notification Period | 1.1.3.7 | 2 (two) years |
| Electronic transmission systems | 1.3 | In written form and delivery in person, by mail or by courier |
| Law of the Contract | 1.4 | The contract is implemented in accordance with the laws of the Republic of Serbia. Everything that is not regulated by this contract is governed by the provisions of the Law on Public Procurement ("Official Gazette of RS", No. 91/19), the Law on Obligations ("Official Gazette of the SFRY No. 29/78, 39/85, 45/89 decision of the USJ and 57/89, "Official Gazette of the SFRY", No. 31/93, "Official Gazette of the SCG" No. 1/2003 - Constitutional Charter and "Official Gazette of the RS" No. 18/2020), of the Law on Planning and Construction ("Official Gazette of the RS", no. 72/2009, 81/2009 - corrected, 64/2010 - decision US, 24/2011, 121/2012, 42/2013 - decision US, 50/ 2013 - US decision, 98/2013 - US decision, 132/2014, 145/2014, 83/2018, 31/2019, 37/2019 - other laws, 9/2020 and 52/2021), Special Regulations on Construction ("Official Gazette of the SFRY" No. 18/77), Rulebook on the content and method of performing the technical inspection of the facility, the composition of the commission, the content of the commission's proposal on determining the suitability of the facility for use, observation of the soil and the facility during construction and using and minimum warranties periods for certain types of the facilities ("Official Gazette of RS", no. 27/2015, 29/2016 and 78/2019) and other legislations that regulate the subject matter. In the event of a conflict between the provisions of this contract and the Law on Public Procurement ("Official Gazette of RS", No. 91/19), the Law on Public Procurement takes precedence. |
| Ruling language | 1.4 | The language of the Agreement is Serbian and English. In case of dispute, the Serbian language version is authoritative. |
| Language for communications | 1.4 | Serbian language and English language (bilingual). |
| Time for access to the Site | 2.1 | No later than the Commencement Date |
| Engineer’s Duties and Authority | 3.1 | In accordance with Particular Conditions of Contract. |
| Amount and currency of the Performance Security | 4.2 | 10% of the Contract Price The Performance Security will be in the form of a performance bond in the amount (s) of 10% (ten) percent of the Accepted Contract Amount and in the same currency (ies) of the Accepted Contract Amount. |
| Duration of Performance Security | 4.2 | In accordance with Form of performance security (sample form): 70 days after the expected expiry of the Defects Notification Period for the Works. |
| Normal working hours | 6.5 | 07 am-23pm, all calendar days |
| Delay damages for the Works | 8.7 | 0,05% of the Contract Price per day |
| Maximum amount for delay damages | 8.7 | 5% of the Contract Price |
| Rate for overhead charges and profit | 13.5 (b) ii | 14% |
| Total advance payment | 14.2 | 20% of the Accepted Contract Amount payable in the currencies and proportions in which the Accepted Contract Amount is payable |
| Number and timing of advance payment | 14.2 | One instalment, paid upon delivery of an approved Performance Security and the Advance Payment Guarantee in terms approved by the Employer. |
| Reimbursement of the advance payment | 14.2 | The advance payment shall be repaid by way of deductions of percentage of the advance payment in relation to the Contract price of each Payment Certificate (including First Payment Certificate) |
| Percentage of retention | 14.3 | 3% of the Interim Payment Certificates |
| Limit of Retention Money | 14.3 | 3% of the Contract Price |
| Currencies of Payment | 14.15 | Currency of the European Economic and Monetary Union (EUR) if Contractor is non-resident of Serbia and the Serbian dinar (RSD) if Contractor is resident of Republic of Serbia, average exchange rate of NBS on the day of issuing of invoice (IPC) if the Contractor is resident of the Republic of Serbia. |
| Deadline for the submission of insurance |  |  |
| (a) Certificate of insurance | 18.1 | 5 days after the Commencement Date |
| (b) Relevant policies | 18.1 | 5 days after the Commencement Date |
| Insurance for Works and Contractor's Equipment | 18.2 | to the full amount |
| Minimum amount of third-party insurance | 18.3 | 5,000,000 euros per individual case and in total |
| Professional liability insurance policy for the economic operator as a contractor, all in accordance with the Rulebook on Conditions for Professional Liability Insurance ("Official Gazette of the RS", no. 40/2015), for the entire duration of the contract. (Limits) | 18.5 | Minimum one policy in the minimum amount of 500.000 euros if the tenderer is a company or another legal entity, or 150.000 euros if it is an entrepreneur. In the case the contract is awarded to a group of tenderers, it is sufficient for one member of the group of tenderers to fulfill the stated requirement. All other members of the group of tenderers should fulfill this requirement in terms of the minimum amount of the insured sum in accordance with Article 6 of the Rulebook on Conditions for Professional Liability Insurance ("Official Gazette of the RS", no. 40/2015). |
| Appointment of the Dispute Adjudication Board | 20.2 | 14 days after the Commencement Date. The DAB shall comprise 3 members |
| Appointing entity | 20.3 | If there is no agreement between the party: The President of the International Federation of Consulting Engineers (FIDIC) or a person appointed by the President of the International Federation of Consulting Engineers (FIDIC). |