## PARTICULAR CONDITIONS OF CONTRACT

These conditions amplify and supplement, the General Conditions governing the contract. Unless the Particular Conditions provide otherwise, those General Conditions remain fully applicable. The numbering of the Clauses of the Particular Conditions is not consecutive but follows the numbering of the Clauses of the General Conditions.

| Sub-Clause |  |
| --- | --- |
| 1 | GENERAL PROVISIONS |
| 1.1 | Definitions |
| 1.1.1.3 | Shall be amended as follows: “Letter of Acceptance” means the Contract Agreement and the date of issuing or receiving the Letter of Acceptance means the date of signing the Contract Agreement. |
| 1.1.1.7 | Schedules shall comprise also the Forms included in Tender Documents: - the Tender; - the Statement Form for Staff Working at Height; - the Statement Form for Key Technical Personnel; - the Statement Form for Technical Equipment; - the Statement of integrity; - the Environmental and Social Covenant; -the Technical conditions, consisting of Work Program, Method and Organization, and Quality Assurance System; - the Appendix to the financial offer; - the Form on Manufacturers of Materials and Equipment; - Employer’s BIM Requirements for Contractor; - Form of dispute adjudication board agreement |
| 1.1.6.10 | “Bank” means the Council of Europe Development Bank CEB” (whether acting on its own account or in its capacity as administrator of trust funds provided by other donors) named in the Contract Data. |
| 1.1.6.11 | “Fraud and Corruption” means any act that constitute one or more of the practices defined in CEB’s Guideline 2011. |
| 1.4 | Law and Language Add at the end of this Sub Clause: “Execute and operate the Contract in accordance with the laws of the Republic of Serbia. Everything that is not regulated by this contract is governed by the provisions of the Law on Public Procurement ("Official Gazette of RS", No. 91/19), the Law on Obligations ("Official Gazette of the SFRY No. 29/78, 39/85, 45/89 decision of the USJ and 57/89, "Official Gazette of the SFRY", No. 31/93, "Official Gazette of the SCG" No. 1/2003 - Constitutional Charter and "Official Gazette of the RS" No. 18/2020), of the Law on Planning and Construction ("Official Gazette of the RS", no. 72/2009, 81/2009 - corrected, 64/2010 - decision US, 24/2011, 121/2012, 42/2013 - decision US, 50/ 2013 - US decision, 98/2013 - US decision, 132/2014, 145/2014, 83/2018, 31/2019, 37/2019 - other laws, 9/2020 and 52/2021), Special Regulations on Construction ("Official Gazette of the SFRY" No. 18/77), Rulebook on the content and method of performing the technical inspection of the facility, the composition of the commission, the content of the commission's proposal on determining the suitability of the facility for use, observation of the soil and the facility during construction and using and minimum warranties periods for certain types of the facilities ("Official Gazette of RS", no. 27/2015, 29/2016 and 78/2019) and other legislations that regulate the subject matter.” In the event of a conflict between the provisions of this contract and the Law on Public Procurement ("Official Gazette of RS", No. 91/19), the Law on Public Procurement takes precedence. The Serbian language and English language are ruling. In case of dispute, the Serbian language version is authoritative. Employer’s and Contractor’s documents required with reference to building documentation, licenses and permits under Serbian Rules shall be made in Serbian Language, but for the sake of the Contract they shall be translated into English when required by the Engineer. Day to day communication on the site may be in Serbian or English, but all written communication, minutes of meeting, notices and any other contractual communication shall be in English as well as in Serbian, in which case the Contractor shall be responsible for translation. The Contractor shall have a sufficient number of competent interpreters available.” |
| 1.5 | Priority of Documents The following documents shall be deemed to form and be read and construed as part of this Agreement, in the following order of precedence: - the Contract Agreement; - the Letter of Acceptance - the Tender; - the Appendix to Tender (if any); - the Particular Conditions of Contract; - the General Conditions of Contract; - the Technical Specifications; - the Drawings; - the Schedules; - any other documents forming part of the Contract. |
| 1.6 | Contract Agreement In the second sentence of this Sub-Clause delete “annexed to the Particular Conditions” and substitute “included in the Tender Documents”. |
| 1.13 | Compliance with Laws In Sub-Clause 1.13, add the following paragraph: “(c) The Employer shall obtain the building permits for the Permanent Works, and will pay for all necessary permits and approvals related to these permits.” |
| 1.15 | Inspections and Audit by the Bank Ad as a new Sub-Clause 1.15: This Sub-Clause shall not limit liability in any case of fraud, deliberate default or reckless misconduct by the defaulting Party. The following is added: “The Contractor shall permit and shall cause its subcontractors and subconsultants to permit, the Bank and/or persons appointed by the Bank to inspect the Site and/or the accounts and records relating to the procurement process, selection and/or contract execution, and to have such accounts and records audited by auditors appointed by the Bank if requested by the Bank. The Contractor’s and its Subcontractors’ and subconsultants’ attention is drawn to Sub-Clause 15.6 (Fraud & Corruption) which provides, inter alia, that acts intended to materially impede the exercise of the Bank’s inspection and audit rights constitute a prohibited practice subject to contract termination (as well as to a determination of ineligibility pursuant to the Bank’s prevailing sanctions procedures).” |
| 2.4 | Employer Financial Agreement The following sub-paragraph is added at the end of Sub-Clause 2.4: "In addition, if the Bank has notified to the Borrower that the Bank has suspended disbursements under its loan, which finances in whole or in part the execution of the Works, the Employer shall give Notice of such suspension to the Contractor with details including the date of such notification, with a copy to the Engineer, within 7 days of the Borrower having received the suspension notification from the Bank. If alternative funds will be available in appropriate currencies to the Employer to continue making payments to the Contractor beyond a date, 60 days after the date of Bank notification of the suspension, the Employer shall provide reasonable evidence in his Notice of the extent to which such funds will be available.” |
| 3 | THE ENGINEER |
| 3.1 | Engineer's Duties and Authority Insert at the end of this Sub-Clause: "The Еngineer shall perform, among other duties and authority, the role of expert supervision, in accordance with the Rulebook on the content and management of expert supervision ("Official Gazette of RS", no. 22/2015 and 24/2017). The Engineer shall obtain the Employer’ written approval before exercising its authority under the following sub-clauses of these Conditions: - Sub-clause 3.2: delegation of authority; - Sub-clause 3.5: agreeing or determining any matter, which will increase the Contract Price; - Sub-clause 4.4: giving consent to a Sub-contractor for works that should have been carried out by a different Sub-contractor named in the Contract; - Sub-clause 8.4: agreeing or determining an extension of the Time for Completion; - Sub-clause 10.1: issuing any Taking-Over Certificate; - Sub-clause 11.9: issuing the Performance Certificate - Clause 13: instructing a Variation which is expected to increase the Contract Price or in any substantial way change the character or quality of the Works; - Sub-clause 14.13: issuing the Final Payment Certificate Notwithstanding the obligation, as set out above, to obtain approval, if, in the opinion of the Engineer, an emergency occurs affecting the safety of life or of the Works or of adjoining property, he may, without relieving the Contractor of any of his duties and responsibilities under the Contract, instruct the Contractor to execute all such work or to do all such things as may, in the opinion of the Engineer, be necessary to abate or reduce the risk and in such event the Engineer should inform immediately on the same day of such documented instruction by letter to the Employer and the Bank. The Contractor shall forthwith comply, despite the absence of approval of the Employer, with any such instruction of the Engineer. The Engineer shall determine an addition to the Contract Price, in respect of such instruction, in accordance with Clause 13.3 [Variation Procedure] and shall notify the Contractor accordingly, with a copy to the Employer.” |
| 3.5 | Determinations Add the following words after the second sentence: “provided always that, with reference to Sub-Clause 3.1, item (ii), the Engineer has no authority to make a fair determination of any new rate or price,” The second paragraph shall become the third paragraph. Insert a new, second paragraph as follows: “In preparation for the determination of a new rate or price, the Engineer shall submit his proposal together with substantiating documents, prepared in accordance with Sub-Clause 12.3, to the Employer. If the Contractor has proposed a new rate or price the Engineer’s submission shall be accompanied by an evaluation of the Contractor’s proposal, including any comments or modifications by the Engineer. The Employer will establish a committee which will evaluate the Engineer’s submission, and which will determine any new rate or price based on documented market proposals from various suppliers. Any new rate or price thus determined by the committee will be informed by the Employer to the Engineer. If within 21 days from the date of receipt of Engineer’s written proposal the Employer neither submits its comments to the Engineer nor approves the rate or price proposed by the Engineer, then the new rate or price proposed by the Engineer shall be deemed to be approved.” In the third paragraph delete the first sentence and insert the following: “The Engineer shall give notice to the Contractor of each determination by the committee of a new rate or price. For each agreement or determination by the Engineer on any other matter, the Engineer shall give notice to both Parties, with supporting particulars.” |
| 3.6 | Management Meetings Add as new Sub-Clause 3.6: “The Engineer or the Contractor's Representative may require the other to attend a management meeting in order to review the Contractor’s implementation arrangements and programming for the Works. The Engineer and the Contractor's Representative may invite others to attend. The Engineer shall prepare minutes of the discussions held at management meetings. The Engineer and the Contractor’s Representative as a true record shall sign such minutes. The Engineer shall supply copies of the minutes to those attending the meeting and to the Employer. In the minutes, responsibilities for any actions to be taken shall be in accordance with the Contract. These records shall not be construed as any agreement, approval, check, consent, decision, determination, examination, instruction, notice, proposal or request by the Engineer.” |
| 3.7 | Facilities for the Engineer Add as a new Sub-clause 3.7: “The Contractor will ensure site offices for the Engineer and its staff.” |
| 4 | THE CONTRACTOR |
| 4.2 | Performance Security Add at the end of sub-clause 4.2 the following paragraphs: The Contractor shall obtain (at its cost) a Performance Security in the amounts stated in the Contract Data and denominated in the currency(ies) of the Contract or in a freely convertible currency acceptable to the Employer. If amounts are not stated in the Contract Data, this Sub-Clause shall not apply. “Whenever, the Engineer determines an addition to the Contract Price amounting to more than ten percent (10%) of the accepted Contract Price Amount, the Contractor, at the Engineer’s written request, shall promptly increase the value of the bank guarantee by an equal percentage.” |
| 4.3 | Contractor’s Representative Add at the end of this Sub-Clause: “The Project Manager on site shall be appointed as the Contractor’s Representative. If any of these persons is not fluent in this language, the Contractor shall make competent interpreters available during all working hours in a number that the Engineer consider to be sufficient for those persons to properly perform their delegated powers, function and/or authority. If the Contractor’s Representative is not authorised to lead construction works in accordance with Serbian legislation, the Contractor shall appoint a person with such authorisation to work with the Contractor’s Representative.” |
| 4.8 | Safety Procedures Add the following sub-paragraph to end of this Sub-Clause: “(f) comply with Serbian legislation for Safety at Work (g) The Site shall be a “hard hat” site and safety hats shall be worn at all times. Other protection clothing etc. shall be available and worn as required. (h) The Contractor shall comply with all applicable current legislation, regulations and specifications, with respect to all measures, operations and administrative steps required for the full protection and safeguarding of the environment. Safety issues shall be on the agenda of all site meetings and plans shall be jointly agreed between the Engineer and the Contractor’s Representative for minimising the risks of unsafe events and working practices in forthcoming work. The safety procedures shall be approved by the Engineer.” |
| 4.9 4.14 | Quality Assurance Add after last paragraph: “The Quality Assurance system shall: (a) ensure that all materials and equipment delivered to site are traceable in terms of origin. (b) include procedures for checking compliance and filing of compliance certificates, and (c) include an electronic and paper filing system for storing all certificates and delivery dates (a document control system). The Quality Assurance Plan shall be submitted not later than 15 days after the Commencement Date.” Avoidance of Interference At the end of this Sub-Clause add the following: “Due to the nature of the Site location, being in the centre of Belgrade, and due to the anticipated congested traffic conditions at this location, all operations necessary for the execution and completion of the Works and the remedying of any defects therein shall be carried on so as not to interfere unnecessarily or improperly with: - The convenience of the public, or - The access to, use and occupation of public or private roads and footpaths of properties whether in the possession of the Employer or of any other person. The Contractor shall save harmless and indemnify the Employer in respect of all claim, proceedings, damages, costs, charges and expenses whatsoever arising out of, or in relation to, any such matters insofar as the Contractor is responsible therefore.” |
| 4.21 | Progress Reports At the end of this Sub-Clause add the following: “The monthly progress reports shall be prepared in Serbian and translated into the English language if required by the Engineer at the Contractor’s cost. The Contractor’s Representative shall keep a daily diary (named Construction Diary) in duplicate. The diary shall as a minimum record: - Working hours - Brand and quantity of Goods/Materials delivered to the Site that day - Certificates for that Goods/Materials - Method of works - Method of care and protection of preformed works - List of Contractor’s Key Staff present on the Site with details on time spent on the Site for each Key Staff - The number of persons employed on site, broken down by trade and grade - The Contractor’s Equipment in use on the Site - Work achieved during that day and quality control of works - Incidents - Problems encountered - Weather conditions The original and the copy of the construction diary shall be signed by the Contractors Representative and the Engineer on daily basis. The Engineer shall keep the signed copy and the Contractor’s Representative the original. The dairy shall be in the Serbian language and translated to English when required by the Engineer. The Contractors Representative shall prepare a monthly report in a format to be agreed with the Engineer. The report shall be issued to the Engineer before the 10th of the following month. The report shall be in the Serbian language and translated into English language if required by the Engineer at the Contractor’s cost. The Contractor shall maintain and keep up to date all official records and reports required under Serbian law. The Contractor undertakes to properly record all changes and required data related to the execution of works in BIM technology during the execution of the works, and in everything according to the document related to the requirements of the Employer regarding BIM technology." The Contractor will be provided at no cost the initial BIM design data by the Design Consultant who has prepared the final design for the and will further develop the BIM model in line with the requirements of the project. |
| 6 | STAFF AND LABOUR |
| 6.5 | Working Hours Add as new Sub-Clause 6.5: “If the Contractor intends to work outside the working hours defined in the Appendix to Tender, he shall obtain permission from the Engineer. Such permission shall be requested a week in advance in order to obtain approval by the relevant authorities. This permission will only be given when granted by the relevant authorities.” |
| 6.7 | Health and Safety Insert at the beginning of Sub-Clause 6.7, the following: “The Contractor shall familiarise himself with the relevant sections of the design including possible Environmental Impact Assessment prepared for the project. The Contractor shall incorporate appropriate recommendations and obligations made in this documentation in his Health and Safety Plan, as specified in this Sub-clause 6.7 and Serbian Legislation. Prior to commencement of Work, the Contractor shall submit a Health and Safety Plan providing a detailed description of his proposed methods for ensuring safety of the Works during all stages of construction and commissioning. The health and safety Plan shall set out all the health and safety requirements: (i) stated in the Specification; (ii) that comply with all the Contractor’s health and safety obligations under the Contract; and (iii) that are necessary to effect and maintain a healthy and safe working environment for all persons on the Site and other places (if any) where the Works are being executed. Construction of the Works shall not commence until a Notice of No-objection issued by the Engineer and Employer, is given to the health and safety Plan.” |
| 6.8 | Contractor’s Superintendence At the end of Sub-Clause 6.8, insert the following paragraph: “A sufficient proportion of the Contractor's superintending staff shall also have a working knowledge of both oral and written Serbian language, or the Contractor shall have a sufficient number of competent interpreters available on Site during all working hours, to ensure the proper transmission of instructions and information.” |
| 6.10 | Records of Contractor’s Personnel and Equipment At the end of the Sub-Clause add the following: “The Contractors personnel and equipment at site shall be recorded daily in the Construction Diary according to Sub-Clause 4.21. All staff and labor on the Site shall be provided with identification as follows: (a) Identification badges incorporating the name and photographs of the person and the name of the direct employer (Contractor, Subcontractor, etc.) (b) Hard hats with the name of the direct employer.” |
| 6.11 | Disorderly Conduct Add as separate paragraphs at the end of Sub-Clause 6.11: “With respect to the Contractor, Sub-contractors and all their respective employees: (a) The Contractor shall not allow the bringing, selling or consumption of alcoholic drinks or drugs on Site; (b) The Contractor shall not allow the bringing, selling or illegal carrying of weapons and ammunition on Site; (c) The Contractor shall bear any additional cost and expenses (taxes, duties, penalties, insurance, overtime, etc.) arising as a consequence of contravention of this Clause by the Contractor’s personnel.” |
|  | Add new Sub-Clauses 6.12 through 6.17 as follows: |
| 6.12 | Festivals and Religious Customs “In dealing with his staff and labour, the Contractor shall respect the Country's recognised festivals, days of rest and religious or other customs in accordance with Serbian legislation.” |
| 6.13 | Employment of Foreign Personnel and Labour “The Contractor may bring into the Country any foreign personnel who are necessary for the execution of the Works to the extent allowed by the applicable Laws. The Contractor shall ensure that these personnel are provided with the required residence visas and work permits. The Employer will, if requested by the Contractor, use his best endeavors in a timely and expeditious manner to assist the Contractor in obtaining any local, state, national or government permission required for bringing in the Contractor’s personnel. The Contractor shall be responsible for the return of these personnel to the place where they were recruited or to their domicile. In the event of the death in the Country of any of these personnel or members of their families, the Contractor shall similarly be responsible for making the appropriate arrangements for their return or burial.” |
| 6.14 | Measures against Insect and Pest Nuisance “The Contractor shall at all times take necessary precautions to protect all staff and labour employed on the Site from insect nuisance, rats and other pests and reduce the dangers to health and the general nuisance by the same.” |
| 6.15 | Epidemics or pandemics “In the event of outbreak of illness of an epidemic or a pandemic nature, the Contractor shall comply with and carry out such regulating orders and requirements as may be made by the Government of the Republic of Serbia or the local medical or sanitary authorities for the purpose of dealing with and overcoming the same.” |
| 6.16 | Burial of the Dead “The Contractor shall make the necessary arrangements for the transport, to any place as required for burial, of any of his expatriate employees or members of their families who may die in the Country. The Contractor shall also be responsible, to the extent required by local regulations, for making any arrangement with regard to burial of any of his local employees who may die while engaged upon the Works execution.” |
| 6.17 | Supply of Water “The Contractor shall provide on the Site an adequate supply of drinking and other water for the use of his staff and labour.” |
| 6.18 | Forced or Compulsory Labour Ad as new sub-clause 6.18: The Contractor shall not employ forced labour, which consists of any work or service, not voluntarily performed, that is exacted from an individual under threat of force or penalty, and includes any kind of involuntary or compulsory labour, such as indentured labour, bonded labour, or similar labour-contracting arrangements. The Contractor shall not employ persons who have been subject to trafficking. Trafficking in persons is defined as the recruitment, transportation, transfer, harbouring or receipt of persons by means of the threat or use of force or other forms of coercion, abduction, fraud, deception, abuse of power, or of a position of vulnerability, or of the giving or receiving of payments or benefits to achieve the consent of a person having control over another person, for the purposes of exploitation.” |
| 6.19 | Non-Discrimination and Equal Opportunity Ad as new sub-clause 6.19: Contractor shall not make employment decisions on the basis of personal characteristics unrelated to inherent job requirements. The Contractor shall base the employment relationship on the principle of equal opportunity and fair treatment and shall not discriminate with respect to aspects of the employment relationship, including recruitment and hiring, compensation (including wages and benefits), working conditions and terms of employment, access to training, job assignment, promotion, termination of employment or retirement, and discipline. Special measures of protection or assistance to remedy past discrimination or selection for a particular job based on the inherent requirements of the job shall not be deemed discrimination. The Contractor shall provide protection and assistance as necessary to ensure non-discrimination and equal opportunity, including for specific groups such as people with disabilities.” |
| 6.20 | Employment Records of Workers Ad as new sub-clause 6.20: The Contractor shall keep complete and accurate records of the employment of labour at the Site. The records shall include the names, ages, genders, hours worked, and wages paid to all workers. These records shall be summarized on a monthly basis and submitted to the Engineer. These records shall be included in the details to be submitted by the Contractor under Sub-Clause 6.10 [Contractor Records] |
| 7 | PLANT, MATERIALS AND WORKMANSHIP |
| 7.4 | Testing At the end of this Sub- Clause add the following: “Detailed requirements and procedures for the tests are stated in Technical Documentation and plans, and shall be performed by a “Serbian Authorised, independent third Party” employed and paid by Contractor in accordance with Serbian Rules. Should any additional tests be required these will be instructed to the Contractor by the Engineer and shall similarly be performed by a Serbian authorised, independent third party. All costs for the Engineer (including one representative of the Employer and the Final User respectively) for attending tests or inspections shall be borne by the Contractor if the tests/inspections are not within the surroundings of the Site (20 km).” |
| 8 | COMMENCEMENT, DELAYS AND SUSPENSION |
| 8.1 | Commencement of Works The Engineer shall give a Notice to the Contractor stating the Commencement Date, not less than 14 days before the Commencement Date. The Notice shall be issued promptly after the Engineer considers that the following condition have been fulfilled: (a) signature of the Contract Agreement by both Parties, and if required, approval of the Contract by relevant authorities of the Republic of Serbia; (b) delivery to the Contractor of reasonable evidence of the Employer’s financial arrangements (under Sub-Clause 2.4 [Employer’s Financial Arrangements]); (c) subject to what is stated in the entry for Sub-Clause 2.1 in the Contract Data, effective access to and possession of the Site given to the Contractor together with such permission(s) under (a) of Sub-Clause 1.13 [Compliance with Laws] as required for the commencement of the Works (d) receipt by the Contractor of the Advance Payment under Sub-Clause 14.2 [Advance Payment] provided that the Advance Payment Guarantee and Performance Security, have been delivered by the Contractor. |
| 8.4 | Extension of Time for Completion Insert at the end of Sub-Clause 8.4: “Extension of Time for Completion does not by itself entitle the Contractor to any additional payment. The Contractor shall not be entitled to a separate Extension of Time for Completion for each one of several causes of delay running concurrently but only for the actual period of delay determined by the Engineer irrespective of the causes contributing to produce such delay. If one of several causes of delay operating concurrently is due to the fault of the Contractor and would itself irrespective of the concurrent causes have delayed the completion of the Works or part thereof no Extension of Time for Completion shall be granted for the period of such delay.” |
| 8.6 | Rate of Progress At the end of Item 2, add: “Extension of working hours shall include working in three shifts. The Employer may, in the event provided under Item 1, order the Contractor to work in three shifts”. |
| 8.10 | Payment for Plant and Materials in Event of Suspension In Sub-Clause 8.10, in sub-paragraph (b), after the Contractor, insert: “has presented satisfactory evidence that the Plant and/or Materials are fully owned by the Contractor and are not subject to any retention of title end” |
| 9 | TESTS ON COMPLETION |
| 9.1 13 13.8 | Contractor’s Obligations At the end of this Sub-Clause add the following: “Should any Tests on Completion be required these will be instructed to the Contractor by the Engineer and shall be performed by a Serbian authorised, independent third party.” VARIATIONS AND ADJUSTMENT Instead of the text from point 13.8, the following text is stated: "If during the execution of the works, there is a change in market conditions, i.e. until the price increase of the elements on the basis of which the contracted price was formed, the Contractor has the right to the price difference, which will be calculated using a sliding scale based on the increase in the index, in accordance with the official reports of the Statistical Office of the Republic of Serbia. The difference in price will be calculated only if there is a reduction or increase in prices by more than 5%, only for an amount that exceeds 5%, and if the said price increase did not occur after the expiration of the agreed term for the performance of works. The base date is the date of submission of the tender in the public procurement procedure, and the final calculation date is the contracted deadline for the performance of the works. The necessary indexes for the price difference can be found in the official reports of the Statistical Office of the Republic of Serbia- monthly bulletin for the month of the accounting period. The coefficient of correction of the agreed price will be calculated according to the formula: k =Pf+ Pr* Pc/Pso + Pm*M/Mo+Pen* E/Eo Pf= fixed part in the total offered price = 20% of the total contracted price; Pr= percentage of labor participation in the total offered price; Pm= percentage of the participation of elements and materials for construction in the total offered price; Pen= percentage of participation of energy sources in the total offered price; Ps= growth index of nominal wages of employees for the calculation month; Pso= growth index of nominal wages of employees for the base month; M= index of growth of elements of materials for installation in construction for the calculation month; Mo= index of growth of elements of materials for installation in construction for the base month; E= producer price growth index - liquid fuels and lubricants for the calculation month; Eo= producer price growth index - liquid fuels and lubricants for the base month. Calculation of remuneration to the Contractor for the performed works will be done according to the formula: For the coefficient value: k < 0.95 N= (k+0.05)*U For the coefficient value: 0.95 ≤ k ≤ 1.05 N= U For the coefficient value: k > 1.05 N= (k-0.05)*U N= amount for payment of performed works; U= the amount of performed works according to the agreed prices. In the case from the previous paragraph, the Contractor is obliged to provide an analysis of the contracted price by the position of the works, which will contain the price of materials, the price of labour, energy, and a fixed part for each position individually. The Contractor envisages the possibility of defining in more detail the elements that participate in the formation of the total contracted price according to the price indices of the Statistical Office of the Republic of Serbia. The submitted price analysis needs to be approved by the Engineer and the Employer.” |
| 14 | CONTRACT PRICE AND PAYMENT |
| 14.2 | Advance payment The advance payment shall be repaid by way of deductions of percentage of the advance payment in relation to the Contract price of each Payment Certificate (including First Payment Certificate). "The Contractor shall obtain (at the Contractor’s cost) an Advance Payment Guarantee in amounts and currencies equal to the advance payment and shall submit it to the Employer with a copy to the Engineer. This guarantee shall be issued by reputable bank or financial institution selected by the Contractor and shall be based on the sample form annexed to the Particular Conditions or in another form agreed by the Employer (but such agreement shall not relieve the Contractor from any obligation under this Sub-Clause).” 14.3 Application for Interim Payment Certificates At the end of subpoint 14.3, the following paragraphs should be added: “In addition to the above, the condition for payment of Interim Payment Certificates is a positive (monthly) report on the services performed in BIM technology in everything according to the document related to the requirements of the Employer in terms of BIM technology, which report was approved by the Employer and Engineer.” |
| 14.9 | Payment of Retention Money At the end of Sub-Clause 14.9 add the following paragraphs: “If proposed by the Contractor and approved by the Employer, the second half of the Retention Money will be certified for payment after: (a) the Engineer has issued a Taking-Over Certificate for the whole of the Works, and (b) the Employer has received a Retention Money Bank Guarantee in the amount of half of the Retention Money in a form, and from a Bank, approved by the Employer. The Retention Money Guarantee shall provide a surety for the second half of the Retention Money for the whole of the Works held for the rectification of defects arising during the remainder of the Contract Period and the completion of any remaining work to be executed under Clause 11 [Defects Liability] or Clause 12 [Measurement and Evaluation]. The terms and conditions for the Retention Money Guarantee shall be the same as those stated in sub-clause 4.2 for a Performance Security.” 14.11 Application for Final Payment Certificate At the end of subpoint 14.11, the following paragraphs should be added: In addition to the above, the condition for payment of the Final Payment Certificate is a positive report on the services performed in BIM technology in everything according to the document related to the requirements of the Employer in terms of BIM technology, which report has been approved by the Employer and Engineer. |
| 15 | TERMINATION BY EMPLOYER |
| 15.2 | Contract Termination by Employer In 1st paragraph, line d) add as follows: “or if persons are engaged without the Employer’s approval, i.e. persons are engaged that have not been registered in accordance with the Contractor’s Bid – Form of Declaration for workers for work at height and Form of Declaration for key technical personnel”. |
| 15.6 | Fraud and Corruption Ad as new sub-clause 15.6: The Bank requires that all Borrowers (including grant beneficiaries), Executing Agencies and Contracting Agencies as well as all firms, entities and individuals bidding for or participating in a Bank-financed activity including, inter alia, applicants, bidders, suppliers, contractors, consultants, personnel, sub-contractors, sub-consultants, service providers and concessionaires (including their respective officers, employees and agents irrespective of whether the agency is express or implied), adhere to the highest ethical standards, and report to the Bank all suspected acts of Fraud & Corruption of which they have knowledge or become aware both, during the bidding process and throughout negotiation or execution of a contract. Fraud & Corruption include acts of: (i) corrupt practices, (ii) fraudulent practices, (iii) coercive practices, and (iv) collusive practices and (v) obstructive practices. The Bank has also entered into agreements with other International Financial Institutions (IFIs) to mutually recognize sanctions imposed by their respective sanctioning bodies. The Bank defines, for the purposes of this provision in the Guidelines 2011. If, in accordance with the Fraud & Corruption Practices if it is determined that at any stage of the procurement or implementation of a contract any firm, entity or individual bidding for or participating in a Bank-financed activity including, inter alia, applicants, bidders, suppliers, contractors, consultants, personnel, sub-contractors, sub-consultants, goods or service providers, concessionaires, Borrowers (including grant Beneficiaries) Executing Agencies or Contracting Agencies (including their respective officers, employees and agents irrespective of whether the agency is express or implied) engaged in a Fraud & Corruption the Bank may: (a) not finance any proposal to award a contract for works, goods or services, and consulting services; (b) suspend disbursement of the operation if it is determined at any stage that an employee, agent or representative of the Borrower, Executing Agency or Employer has engaged in a Prohibited Practice; (c) declare Mis procurement and cancel, and/or accelerate repayment of the portion of a loan or grant earmarked for a contract, when there is evidence that the representative of the Borrower, or Beneficiary of a grant, has not taken the adequate remedial measures (including, inter alia, providing adequate notice to the Bank upon learning of the Prohibited Practice) within a time period which the Bank considers reasonable; (d) issue the firm, entity or individual a reprimand in the form of a formal letter of censure for its behaviour; (e) declare that a firm, entity, or individual is ineligible, either permanently or for a stated period of time to (i) be awarded a contract or participate in activities financed by the Bank; and (ii) be nominated sub-consultant, sub-contractor, supplier or service provider of an otherwise eligible firm being awarded a Bank-financed contract; (f) refer the matter to appropriate law enforcement authorities; and/or (g) impose other sanctions that it deems to be appropriate under the circumstances. The Bank requires that all applicants, bidders, suppliers, and their agents, contractors, consultants, personnel, sub-contractors, service providers and concessionaires permit the Bank to inspect any and all accounts, records and other documents relating to the submission of bids and contract performance as well as to have them audited by auditors appointed by the Bank. Applicants, bidders, suppliers, and their agents, contractors, consultants, sub-contractors, sub-consultants, service providers and concessionaires shall fully assist the Bank with its investigation. The Bank also requires that all applicants, bidders, suppliers, and their agents, contractors, consultants, personnel, sub-contractors, sub-consultants, service providers and concessionaires: (i) maintain all documents and records related to the Bank-financed activities for seven (7) years after completion of the work contemplated in the relevant contract; and (ii) deliver any document necessary for the investigation of allegations of Prohibited Practices and make available employees or agents of the applicants, bidders, suppliers and their agents, contractors, consultants, personnel, sub-contractors, sub-consultants, service providers or concessionaires with knowledge of the Bank-financed activities to respond to questions from Bank personnel or any properly designated investigator, agent, auditor or consultant relating to the investigation. If the applicant, bidder, supplier and its agent, contractor, consultant, personnel, sub-contractor, sub-consultant, service provider or concessionaire fails to cooperate and/or comply with the Bank’s request, or otherwise obstructs the investigation, the Bank, in its sole discretion, may take appropriate actions. |
| 16 | SUSPENSION AND TERMINATION BY CONTRACTOR |
| 16.2 | Termination by Contractor The following paragraph is inserted after the first paragraph: “Notwithstanding the above, if the Bank has suspended disbursements under the loan from which payments to the Contractor are being made, in whole or in part, for the execution of the Works, and no alternative funds are available as provided for in Sub-Clause 2.4 [Employer’s Financial Arrangements], the Contractor may by given a Notice suspend work or reduce the rate of work at any time, after receiving the Employer Notice of Bank’s suspension of disbursement under Sub-Clause 2,4 [Employer arrangement].” |
| 17 | RISK AND RESPONSIBILITY |
| 17.7 | Contractor’s Care of the Existing Facilities Add as new Sub-Clause 17.7 as follows: “The Contractor shall take full responsibility for the care of the parts of the existing facilities (water, sewerage, storm water, telecommunication, electricity etc.) within the Site from the Commencement Date until the date of issuance of Taking-Over Certificate. If any loss or damage happens to any of those parts of the existing facilities while the Contractor is responsible for their care, from any cause not listed in Sub-Clause 17.3 [Employer’s Risks] or for which the Employer is liable under the Contract, the Contractor shall rectify the loss or damage at the Contractor’s risk and cost. The Contractor shall not be held liable and responsible for any of the preparatory construction works in connection with this project and executed by another Contractor under a previous separate tender which should be concluded prior to the initiation of the main construction works”. |
| 18 | INSURANCE |
| 18.2 18.5 | Insurance for Works and Contractor’s Equipment Add at the end of Sub-Clause 18.2: “It shall be the responsibility of the Contractor to notify the insurance company of any change in the nature, extent or programme for the execution of the Works and to ensure adequacy of the insurance coverage at all times during the period of the Contract. The Contractor shall submit evidence of the notification to the Employer.” Add at the end of Clause 18: “The Contractor is obliged to hold a professional liability insurance policy for the economic operator as a contractor, all in accordance with the Rulebook on Conditions for Professional Liability Insurance ("Official Gazette of the RS", no. 40/2015), for the entire duration of the contract, in the minimum values specified in the Appendix to Tender-Financial Offer.” |
| 20 | CLAIMS, DISPUTES AND ARBITRATION |
| 20.6 | Arbitration At the end of this Sub-Clause add the following: “The place of arbitration shall be Belgrade, Serbia. In the case of a dispute between the Employer and a Serbian Contractor the text of sub-paragraph a) shall be deleted and substituted by "the dispute shall be finally settled as set forth in the Arbitration Rules of the Permanent Arbitration Court at the Serbian Chamber of Commerce.” |